SECTION 01 31 19

PROJECT MEETINGS

PART 1 - GENERAL

1.1	RELATED DOCUMENTS

A.	Construction Drawings, Technical Specifications, Addenda, and general provisions of the Contract, including Contract General Conditions and Supplementary General Conditions and other Division 1 Specification Sections, apply to this Section.

1.2	REQUIREMENTS INCLUDED

A.	Preconstruction meeting.

B.	Construction progress meetings.

C.	Pre-installation conferences.

D.	Change Order review meetings

E.	Monthly Progress Payment Meetings

F.	Contract Closeout Meeting

G.	Partnering

1.3	RELATED REQUIREMENTS

A.	Section 01 45 00 - Quality Control:  General requirements for construction quality, to be reviewed at construction progress meetings.

B.	Section 01 32 16 - Construction Progress Schedules:  General requirements for construction progress schedules, to be reviewed at construction progress meetings.

C.	Section 01 32 00 - Construction Progress Documentation:  General requirements for construction progress reports, to be reviewed at construction progress meetings.

D.	Section 01 33 00 - Submittal Procedures:  Status of submittals to be reviewed at construction progress meetings.

E.	Section 01 77 00 - Contract Closeout Procedures:  Contract Completion Review.

1.4	PRECONSTRUCTION MEETING

A.	Preconstruction Meeting:  University's Representative will administer a preconstruction meeting immediately prior to Contractor mobilization onto the project site.

1.	Representatives of the Trustees, the Contractor, selected Subcontractors [OPTIONAL], Architect, and Architect's Consultants [OPTIONAL], and OTHER campus representatives, as appropriate, will attend.

B.	Schedule:  Schedule preconstruction meeting within five days of construction start date established in the Notice to Proceed.

C.	Location:  Preconstruction meeting will be held at a location as directed by the University's Representative.

D.	Agenda:  Preconstruction meeting shall cover the following topics as a minimum.

1.	Special Project Procedures:  Site access restrictions, if any, and requirements to avoid disruption of operations at adjoining facilities.  Present University's requirements for use of premises.

2.	Designation of Key Personnel:  The Trustees, Architect, and Contractor shall designate key personnel and provide a name and address list that includes the following.

a.	The Trustees: The University Representative, Inspector of Record, and others authorized to act in certain capacities for the University.

b.	Architect: Principal and Project Administrator as appropriate.

c. 	Contractor:  Project Manager and Superintendent.

d.	Major subcontractors (as required):  Principal/Project Manager and Superintendent.

e.	Major materials suppliers (as required):  Contact person.

3.	Subcontractors List:  Distribute and discuss list of subcontractors and suppliers.

4.	Coordination:  Review requirements for Contractor's coordination of Work.  Review sequence and schedule for work being performed for University under separate contracts.  Discuss coordination of construction to minimize impacts on continuing Campus operations.

5.	Project Communication Procedures:  Review administrative requirements for written and oral communications.

6.	Construction Schedule:  Distribute and discuss preliminary schedule, initial baseline construction schedule and critical work sequencing of major elements of Work, including coordination of Owner-Furnished/Contractor-Installed (OFCI) products and work under separate contracts by serving utility agencies and companies and University.

7.	Campus and Site Security:  Review requirements for Contractor to develop and implement site security.

8.	Safety Program:  Review requirements for Contractor to develop and implement safety program in compliance with Contract General Conditions and the Owner Controlled Insurance Program (OCIP) [OPTIONAL].

9.	Site Access by University's Representative and Architect:  Review requirements and administrative procedures Contractor may wish to institute for identification and reporting purposes.

10.	Permits and Fees:  Review Contract requirements and review schedule and process for obtaining permits and paying fees.

11.	Project Layout:  Review requirements for laying out of Work, including surveying requirements.

12.	Construction Facilities:  Designate storage and staging areas, construction office areas and parking areas and review site access requirements.

13.	Temporary Utilities:  Requirements for establishing and paying for temporary water, power, lighting and other utility services during construction, including metering and allowances.  Refer to Section

01 51 00 - Temporary Utilities.

14.	Construction Progress Schedules:  Review requirements for preparation and submittal of updating of construction progress and submittals schedules.

15.	Payment Procedures:  Review requirements for preparation and submission of applications for progress payments and for final payment.

16.	Change Procedures:  Review requirements and administrative procedures for Change Orders, Field Instructions and Contractor's Requests for Interpretation (RFI).

17.	Submittals Administration:  Review administrative procedures for shop drawings, product data and samples submittals and review of preliminary Submittals Schedule.

18.	Materials and Equipment:  Review substitution or equal product requirements; review schedule for major equipment purchases and deliveries; review materials and equipment to be provided by University (OFCI products).

19.	Testing and Inspection:  Review tests and inspections to be performed by the following.

a.	Independent testing and inspection agencies.

b.	Manufacturers and installers.

c.	Service utilities and public agencies.

d.	Authorities having jurisdiction (i.e.: State Fire Marshal, Health Dept., etc.).

20.	Operation and Maintenance Data:  Format and content of operation and maintenance manuals.  Refer to Section 01 78 23 - Operation and Maintenance Data.

21.	Instruction of University's Personnel:  Review requirements and scheduling of instruction of personnel specified for Demonstration and Training and in various Sections in Divisions 2 through 17 of the Specifications.

22.	Starting and Adjusting Procedures:  Review requirements of starting and adjusting operating components.  Refer to Section 01 75 00 - Starting and Adjusting.

23.	Project Record Documents:  Review requirements and procedures for preparing, reviewing and submitting project record drawings and specifications.

24.	Construction Cleaning:  Review requirements for progress and final cleaning specified in Section

01 74 00 - Cleaning Requirements.

25.	Contract Closeout:  Review requirements specified in Section 01 77 00 - Contract Closeout Procedures, including procedures for filing of Notice of Completion, final payment and submittals.

1.5	CONSTRUCTION PROGRESS MEETINGS

A.	Construction Progress Meetings:  Meetings will be held to review progress and quality of construction.  The essence of the discussion of each meeting shall be entered into the written record (minutes) of the meeting by the Architect or the University Representative designee.

B.	Schedule:  Construction progress meetings shall be periodically scheduled throughout progress of the Work.  Frequency shall be as determined necessary for progress of Work.  Generally, it is intended that construction progress meetings be held at weekly intervals.

C.	Administration:  The University’s Representative shall make physical arrangements for meetings.  Architect shall prepare agenda with copies for participants, preside at meetings, record minutes and distribute copies within two working days to University's Representative, Contractor, participants and those affected by decisions made at meetings (theses duties may be shared with the University’s Representative or their designee and shall be determined at the preconstruction meeting).  Each discussion item at construction progress meetings shall be numerically identified and carried through subsequent meeting minutes until resolved.

D.	Attendance:  Contractor's project manager and jobsite superintendent shall attend each meeting.  Contractor's subcontractors and suppliers may attend as appropriate to subject under discussion.  University's Representative will attend each meeting. Architect's consultants will also attend, as appropriate to agenda topics for each meeting and as provided in University-Architect Agreement.

E.	Suggested Agenda for Each Construction Progress Meeting:

1.	Meeting Minutes:  Review and correct, if necessary, minutes of previous meeting.

a.	Unless published minutes are challenged in writing prior to the next regularly scheduled progress meeting, they will be accepted as properly stating the activities and decisions of the meeting.

b.	Persons challenging published minutes shall reproduce and distribute copies of the challenge to all indicated recipients of the particular set of minutes.

c.	Challenge to minutes shall be settled as priority portions of "old business" at the next regularly scheduled meeting.

2.	Progress of the Work:  Since last meeting and proposed progress.

a.	Identify potential problems which might impede progress.

b.	Develop corrective measures and procedures, including but not necessarily limited to additional manpower to regain planned schedule.

c.	Review three-week "look ahead" construction schedule (current week plus two weeks ahead), including identification of conflicts and delays.

3.	Ordering Status:  Review status of long-lead time equipment and materials delivery affecting construction progress.

4.	RFI Status:  Review status of Requests for Interpretation (RFI) status.

5.	Submittals Status:  Review shop drawings, product data and samples submission and review status.

6.	Contract Modifications:  Pending Change Orders and Field Instructions.  Review status of proposed substitutions.

7.	Old Business:  Active discussion topics carried over from previous meetings.

8.	New Business:  New topics of discussion affecting construction progress and quality.

9.	Quality Control:  Review maintenance of quality standards and identification of non-conforming Work, including proposed remedial measures to be taken by Contractor.

10.	Project Record Documents:  Status of project record drawings and specifications.

11.	Environmental and Safety Issues.

12.	Other items affecting progress and quality of the Work.

F.	Meeting Time and Location:  As mutually agreed by the Architect, the Contractor, and the University's Representative at on-site location.

G.	Special Meetings:  As necessary, the Architect, the Contractor, or the University's Representative may convene special meetings to discuss specific construction issues in detail and to plan specific activities.

H.	Infrastructure Projects [OPTIONAL]

Contractor is to provide a twelve-week (12-week) look ahead schedule. This schedule shall be updated every two weeks.  The schedule for the first eight (8) weeks shall be firm with no changes or deviations permitted, unless specifically approved or directed by the Trustees. All modifications shall be made in the period of week nine (9) through week twelve (12). The Contractor and the University Representative shall review the twelve-week schedule weekly to identify early any unforeseen conflicts which  could result in schedule changes and shall, to the extent possible, avoid modifications to the initial first eight weeks of the planned schedule.

1.6	PRE-INSTALLATION CONFERENCES

A.	Pre-Installation Conferences:  When specified in individual product specification Sections, convene a pre-installation conference prior to commencing Work specified in individual product Sections.

1.	Require attendance by representatives of firms whose activities directly affect or are affected by Work specified in the Section.

2.	Review conditions of installation, preparation and installation procedures and coordination with related Work and work under separate contracts.

3. Distribute written notice of agenda, meeting time, and location a minimum of 4 calendar days in advance.

    - Agenda:  Review progress of other construction activities and preparations for the particular activity under consideration, including requirements for the following:

      - Contract Documents.

      - Options.

      - Related Change Orders.

      - Review of mockups.

      - Possible conflicts.

      - Compatibility problems.

      - Time schedules.

      - Weather limitations.

      - Manufacturer's written recommendations.

      - Installation procedures.

      - Warranty requirements.

      - Compatibility of materials.

      - Acceptability of substrates.

      - Testing and inspecting requirements.

      - Required performance results.

    - Record significant conference discussions, agreements, and disagreements.

    - Do not proceed with installation if the conference cannot be successfully concluded.  Initiate whatever actions are necessary to resolve impediments to performance of the Work and reconvene the conference at earliest feasible date.

1.7	CHANGE ORDER REVIEW MEETING

A.	Subsequent to the weekly project meeting, a Change order review meeting shall be held to discuss in detail the status of all project change documents. The Contractor, University Representative and Architect (as necessary) shall be in attendance. The following items shall be reviewed at this meeting:

1.	Cost Request Bulletins (both previously issued and necessary for progress of construction).

2.	Change Orders.

3.	Contractor Change Order Requests.

4.	Field Instructions (both previously issued and necessary for progress of construction).

1.8	 MONTHLY PROGRESS PAYMENT MEETING

A. 	A meeting shall be conducted by the University Representative each month prior to Contractor's submission of the Payment Application. This meeting shall be held subsequent to the regular project meeting which precedes the required date for submission of the Payment Application.

1.	Each line item of the payment application shall be reviewed to confirm agreement with the stated percentage complete for the specific item of work. The University Representative will advise Contractor of percentages which are not acceptable and will red-line a copy of the draft payment application indicating necessary revisions required in order for processing of the payment application.

2.	The Contractor shall make necessary revisions in accordance with the red-line comments provided by the University Representative prior to official submission of the payment application.

1.9	CONTRACT CLOSEOUT MEETING

A.	Contract Closeout Meeting:  As specified in Section 01 77 00 - Closeout Procedures.

B.	Approximately four (4) to six (6) weeks prior to the scheduled completion of the Project, for the convenience of the contractor, the University Representative will include in the standard meeting agenda a Project Close-out meeting.

The purpose of the close-out meeting is to produce an action list of major items required to be completed prior to the issuance of the Notice of Completion.

1.	The action list shall assign an action responsibility and a projected action completion date to each item.

2. 	The contractor shall be solely responsible for the timely completion of all required close-out items.

3.	Items to be considered include:

- Punch list

- O & M manuals

- HVAC Balance Report

- Spare Parts/Materials

- Keys/Keying

- Warrantees

- As-built Drawings and Specifications

- As-built Schedule

- State Fire Marshal Inspection

- Elevator Inspection

- Other Required Regulatory Inspections

- Removal of Temporary Facilities

- Final Cleaning and Pest Control

- Landscape Maintenance

- Commissioning/Equipment Startup

- Acceptance

- Notice of Completion

- Final Payment

- Occupancy

1.10	PARTNERING

A.	The Trustees intend to encourage the foundation of a cohesive partnership with the Contractor and the Architect. This partnership will be structured to draw on the strengths of each organization in order to identify and achieve reciprocal goals.  The objectives are effective and efficient contractor performance, intended to achieve completion within budget, on schedule, and in accordance with the plans and specifications.

In order implement to this partnership, the parties are encouraged to organize and attend a partnership development seminar. Participation in such a seminar by the contracting parties shall be totally voluntary. Any associated cost shall be shared equally between the University and the Contractor with no change in the contract price.  [THIS PARAGRAPH IS OPTIONAL]

PART 2 - PRODUCTS

Not applicable to this Section.

PART 3 - EXECUTION

Not applicable to this Section.

END OF SECTION