## Exhibit B
Exhibit B
SMALL PROJECT SCHEDULE OF LUMP SUM FEES and PAYMENT SCHEDULE
|  | ARCHITECTS/ENGINEER'S BASIC SERVICES |  |  |  | How to fill out the Exhibit B Form
Insert date, project, campus and A/E information as indicated in C5 to C8
Date: | 2018-01-04 |  |  |  |  | Fill in the header information.
Project: | [Insert] |  |  |  |  | Insert a construction budget value in D14.
Campus: | [Insert] |  |  |  |  | The resulting SPA fee is calculated automatically!
A/E: | [Insert]
How the SPA fee is calculated
Small Project A/E Fee Basis
|  | Construction |  | A/E | A/E Fee as a % | 8.231% | A CSU standard fee value for a level 2 complexity is used. Use level 2 for ALL SPA work.
|  | Budget |  | Fee (2) | of Construction | 2% | The CSU standard renovation 2% complexity premium is applied to ALL SPA work.
Total A/E Construction Budget |  | 1000000 |  | 130090.4778 | 13.01% | 2.778% | An additional premium (1% to 3%) is applied depending on size of project.
[6 empty] | 13.01% | The SPA A/E fee is the sum of the three elements above.
Small Project A/E Fee Payment Schedule
| Schematic/Preliminary | Construction |  | Construction | Record | 500000 | Low transition. Below this fee value, the low transition fee premium is applied.
Total | Design | Documents | Bidding | Administration | Drawings | 3% | The low transition premium percentage.
100% | 35% | 35% | 0% | 25% | 5%
130090.4778 | 45532 | 45532 | 0 | 32523 | 6503.4778 | Taper percent | Taper transition. The fee value tapers linearly between low and upper transition percentages.
at 25% | - | 11383
at 50% | 22766 | 11383 |  | Monthly |  | 5000000 | Upper transition. Above this fee value, the upper transition fee premium is applied.
at 75% | - | 11383 |  | equal to percentage |  | 1% | The upper transition premium percentage.
at 100% | 22766 | 11383 |  | complete (1)
[6 empty] | 1000000 | Construction value. (Use construction value not total project value.)
Small Project A/E Fee Notes:
#1) Construction Administration fee paid in monthly payments equal to percentage of project's construction completion. | [5 empty] | 27777.7778 | The approximate fee addition over a CSU 'standard'-fee for a renovation level 2 complexity.
#2) Fee percentage follows the CSU standard fee curve with the following modifications: Uses a Type 2 complexity
for all projects, applies a renovation premium on all projects,
and applies a fee percentage increase from 3% to 1% depending upon project construction budget.
Fee Summary
P | 45532 |  | Schematics + Design Development
W | 45532 |  | Construction Documents + Bidding
C | 39026.4778 |  | Const. Admin. + Rec. Dwgs.
TOTAL | 130090.4778 |  | Total PWC

## Rev History
Project Architect/Engineer Agreement Revision History
Rev Date | Comments
2016-03-18 | Agreement: Creation of a dedicated Small Project Agreement. Based on a standard A/E Project Architect Agreement. Key changes: Combines Schematic and Preliminary phases. Directs design to 90% of budget. Exhibits: Revised fee schedule. Uses the CSU standard renovation fee curve as base for all work. Project type distinctions eliminated. All based on a project type 2 renvation with a +3 percent amount for works up to $500,000 and then tapering to standard type 2 renovation fee amount +1% as the work amount exceeds $5,000,000. Above this amount a 1% fee premium is applied.
2018-01-04 | Agreement: General Counsel name updated. Rider A: Section and subsection numbers reset to indicate whole numbers at sections, inadvertently dropped. 'Architect/Engineer shall' added incrementally throughout for consistency. Minor grammar and tense revisions. 2.6.3 Code Analysis and process updates added to reflect current OSFM process. 2.7.4 Deliverables items clarified. 2.9.13 Revised punch list edtion added. 2.10 Provision of BIM model coordinated with Add Services language. 5.1e Code and Peer Review services identifed as provided by Trustees. 6.1 Ownership. The word 'Design' , an intangible, was removed. Electronic equivalents stated as a deliverable. Fee and scope template: Minor grammar changes.