## Cost Recon
Project |  | Renovation & Retrofit | Project No. | CO-999
Contractor |  | ABC Contracting | Contract No. | 12321
Campus |  | CSU Chancellor's Office | Date | 2018-06-04
RECONCILIATION OF PROJECT COSTS
(Use this report for final reporting of project costs for CM at Risk and Collaborative Design-Build projects in accordance with the Contract General Conditions. Amounts in Column K are pulled from Exhibits as described in each category below.)
Line No. | Description of Project Costs |  |  | Amounts
Final Direct Costs
1 | Total Curent Subcontract Amounts (Exhibit "A" - E19) |  |  | 1399000
2 | Total Direct Material Costs (Exhibit "B" - E26) |  |  | 365000
3 | Total Direct Labor Costs (Exhibit "C" - E23) |  |  | 210959.42
4 | Total Other Anticipated Future Costs (Exhibit "D" - C70) |  |  | 0
5 |  |  | Subtotal Final Direct Costs | 1974959.42
Final Fees (including CO fees)
6 | Construction Phase Services per Agreement (Exhibit "E" - enter no.) |  |  | 200000
7 | Overhead & Profit per Agreement (Exhibit "E" - enter no.) |  |  | 150000
8 | Additional Construction Phase Services from Change Orders (Exhibit "F" - E18) |  |  | 0
9 | Additional Fee from Change Orders (Exhibit "F" - G18) |  |  | 44063.99
10 |  |  | Subtotal Final Fees | 2369023.41
Project Savings/Losses Recap
11 | Final GMP Contract Amount through COR No. XX (Exhibit "G" - enter no.) |  |  | 2400000
12 | Total Project Costs (amount from line 10) |  |  | 2369023.41
13 |  |  | Subtotal Project Savings/Losses | 30976.59
Savings Distribution (if any)
14 | Total Project Savings (amount from line 13) |  |  | 30976.59
15 | DB or CM's Share of Savings as % (determined in RFP and contract) |  |  | 25% | This is an example
16 | DB or CM's Share of Savings in $ (Line 14 * 15) |  |  | 7744.1475
17 |  |  | Owner Share of Savings | 23232.4425
Note: This example uses 25% as the # for shared savings. Actual % determined by RFP and contract.
Current Adjusted Contract
17 | Final Contract Amount |  |  | 2400000
18 | Less Owner's Share of Savings |  |  | 23232.4425
19 |  |  | Final Adjusted GMP Amount | 2376767.5575

## Exh A
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "A"
SUBCONTRACT BREAKDOWN
Company Names (Examples shown below) | Trades (Examples shown below) | Original Contract | Change Orders | Current Contract*
Ace Mechanical | Insulation | 150000 | 30000 | 180000
AmTech Elevator Services | Elevators | 100000 | 10000 | 110000
Anning-Johnson Co. | Roofing and Metal Decking | 140000 | 5000 | 145000
BLC Surveying | Survey | 2000 | 0 | 2000
Borbon, Inc. | Painting | 20000 | 2000 | 22000
Calex Engineering Company | Earthwork and Grading | 75000 | 10000 | 85000
Control Air Conditioning Corp. | HVAC and Controls | 200000 | 20000 | 220000
Elite | Scaffolding (Dance Floor) | 30000 | 3000 | 33000
Largo Concrete | Structural Concrete | 175000 | 25000 | 200000
Lawrence W. Rosine, Co. | Flooring | 30000 | 2000 | 32000
Lindero Masonry | Concrete Masonry | 55000 | 5000 | 60000
Mountain States Steel, Inc. | Structural and Miscellaneous Steel | 300000 | 10000 | 310000
| TOTAL | 1277000 | 122000 | 1399000
"Total" values should reconcile back to the first page.

## Exh B
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "B"
DIRECT MATERIAL COSTS
(through mm/dd/yyyy)
Cost Code* | Description |  | Cost
DRM-01536-M ** | Weather Protection | 35000 |  | (Example)
DRM-01538-M | Rough Carpentry | 100000
DRM-01540-M | Progressive Clean up | 10000
(Example No.) | (Example of Descriptions) | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
SCM-22002-M ** | Sewer Permit Fee | 220000
0
0
Total |  | 365000
* Notes:
DRM = Prefix for Direct Material Cost Code
SCM = Prefix for Scope Change Material Cost Code
** Actual Cost Codes provided by the CM
"Total" value should reconcile back to the first page.

## Exh B1
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "B1"
MATERIAL COSTS
(through mm/dd/yyyy)
Note: This page with other supporting documentation is optional and can be used if the campus determines there is more back-up required.
SEE SEPARATE BINDER
for
DETAILED MATERIAL JOB COST LEDGERS
and
COPIES OF MATERIAL INVOICES

## Exh C
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "C"
DIRECT LABOR COSTS
(through mm/dd/yyyy)
Cost Code* | Description |  | Cost
DRL-01536-L ** | Weather Protection |  | 30959.42
DRL-01538-L | Rough Carpentry |  | 50000
DRL-01540-L | Progressive Clean up |  | 20000
(Examples of Code Nos.) | (Examples of Description) |  | (Examples of Cost)
0
0
0
0
0
0
0
0
0
SCL-22003-L ** | Unforseen Utilities/ FI 004 |  | 110000
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Total | 210959.42
* Notes:
DRL = Prefix for Direct Labor Cost Code
SCL = Prefix for Scope Change Labor Cost Code
** Actual Cost Codes provided by the CM
"Total" value should reconcile back to the first page.

## Exh C1
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "C1"
DIRECT LABOR COSTS
(through mm/dd/yyyy)
Note: Additional information is optional and can be used if the campus determines that more back-up is required.
SEE SEPARATE BINDER
for
DETAILED LABOR JOB COST LEDGERS

## Exh D
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "D"
OTHER ANTICIPATED FUTURE COSTS
(excluding costs in future owner change orders beyond COR #XX)
Additional sheets to be used as needed.
Company | Description | Amount
Ace Restoration & Waterproofing, Inc.
Alcal Arcade Contracting, Inc
Alcal Arcade Contracting, Inc.
Ambarch Inc.
American Tile & Brick Veneer, Inc.
AmTech Elevator Services
Architectural SignGroup
Bali Construction, Inc.
Bickerton Iron Works
C.A. Buchen Corporation
Cabrillo Hoist
California Wire Products Corporation
City Commercial Plumbing
CK Wegner
CMC Fontana Steel
Acme Construction (Example) | (40) hours of Laborer Foreman for CAA oversight of issue (Example) | 2000
TOTAL |  | 2000
"Total" value should reconcile back to the first page.

## Exh E
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "E"
CM AGREEMENT AND GMP
The CM can pull this information from existing documents and insert on this page.
SEE SEPARATE BINDER
for
CM Agreement & GMP
"Total" values should reconcile back to the first page.

## Exh F
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "F"
CONTRACTOR'S FEE FROM CHANGE ORDERS
Campus Change Order No. | Contractor Change Order Request No. | Document Ref. | Fee On Direct Work | Construction Phase Services (Ext. O/H) | Fee Total Per COR | Fee Total Per CCO
CCO #1 ** | COR 001 | Permit Fees | 0 | 0 | 0
| COR 002 | FI 003 | -2273.4 | 0 | -2273.4
| COR 003 | FI 005 | -358.4 | 0 | -358.4
| COR 004 | Elective Change | -387.06 | 0 | -387.06
| COR 005 | RFI 096 | -1016.65 |  | -1016.65 | -4035.51
CCO #2 | COR 007 | FI 013 | 48099.5 |  | 48099.5 | 48099.5
0
|  | TOTAL | 44063.99 | 0 | 44063.99 | 44063.99
Note: Information provided in this spreadsheet is used as an example on how to calculate costs.
"Total" values should reconcile back to the first page.
Notes:
CCO# - Contract Change order
COR# - Change Order Request
** Example

## Exh G
CSU Chancellor's Office
Renovation & Retrofit
EXHIBIT "G"
CURRENT GMP CONTRACT AMOUNT
(through COR No. XX)
The CM can pull this information from existing documents and insert on this page.
"Total" values should reconcile back to the first page.